## Slide 1
Stephen Colodner
Office of Program Analysis and Evaluation (PA&E, NA-BA-40)
August 12, 2026
How Fast Do We Burn Money and
When Do We Stop?
Stochastic Phasing and Duration Uncertainty Methodology

## Slide 2: Roadmap
Motivation
Methodology
Monte Carlo Coupling
Interpreting Results
Notes: [0:30] Motivation.
You may have had a tool pulled out from under a model. A license doesn't get renewed, a language version falls out of support, an add-in stops passing security review. When that happens the model doesn't just lose a feature — sometimes it can't be opened at all.
Excel has been on our machines for decades and is already cleared. Excel 365 added LAMBDA, which changes what you can build in it. Everything today rides on a platform that isn't going anywhere.
Don't oversell this. The point is availability and clearance, not that Excel is better than R.

## Slide 3: Motivation
TRACEABILITY
Static output is the bane of the estimator
When a formula becomes a value, the trail back to the data ends.
fx
=AVERAGE(Cost_Data)
↓
1,247,003
— the trail back to Cost_Data ends here
AVAILABILITY
Tool Use Limitations/Handoff
License lapses
A renewal slips and the seat goes dark.
Version sunsets
A language or package drops out of support.
Review tightens
An add-in stops clearing the security baseline.
THE RESULT
Traceable Analysis in Vanilla Excel
Traceability — every formula is a visible, clickable trail back to the source.
Availability — already deployed, already cleared, on every estimator’s machine.
Notes: [0:30] Motivation.
You may have had a tool pulled out from under a model. A license doesn't get renewed, a language version falls out of support, an add-in stops passing security review. When that happens the model doesn't just lose a feature — sometimes it can't be opened at all.
Excel has been on our machines for decades and is already cleared. Excel 365 added LAMBDA, which changes what you can build in it. Everything today rides on a platform that isn't going anywhere.
Don't oversell this. The point is availability and clearance, not that Excel is better than R.

## Slide 4: The Questions Phasing Must Answer
What budget authority is needed in each fiscal year?
How much year-of-execution escalation exposure do we carry?
Is expenditure-to-date consistent with plan, or a warning sign?
If the schedule slips, what happens to the outyear profile?
Notes: [0:30] Motivation.
You may have had a tool pulled out from under a model. A license doesn't get renewed, a language version falls out of support, an add-in stops passing security review. When that happens the model doesn't just lose a feature — sometimes it can't be opened at all.
Excel has been on our machines for decades and is already cleared. Excel 365 added LAMBDA, which changes what you can build in it. Everything today rides on a platform that isn't going anywhere.
Don't oversell this. The point is availability and clearance, not that Excel is better than R.

## Slide 5: Current Practice and Blind Spots
Common approaches: fixed percentage spreads, analogy to one “representative” project, hand-built profiles
All share one assumption: the phasing shape is known
Historical data says otherwise — shape varies project to project
Notes: [0:30] Motivation.
You may have had a tool pulled out from under a model. A license doesn't get renewed, a language version falls out of support, an add-in stops passing security review. When that happens the model doesn't just lose a feature — sometimes it can't be opened at all.
Excel has been on our machines for decades and is already cleared. Excel 365 added LAMBDA, which changes what you can build in it. Everything today rides on a platform that isn't going anywhere.
Don't oversell this. The point is availability and clearance, not that Excel is better than R.

## Slide 6: Why This Is A Problem in Early Estimates
Three Concrete Failure Modes:
Budget formulation: deterministic profile → point annual requests → no basis for reserves phasing
Escalation: back-loaded reality vs. front-loaded plan = under-escalated estimate
Execution review: "behind plan" may be within normal shape variation — or not; no way to tell without a distribution
Notes: [0:30] Motivation.
You may have had a tool pulled out from under a model. A license doesn't get renewed, a language version falls out of support, an add-in stops passing security review. When that happens the model doesn't just lose a feature — sometimes it can't be opened at all.
Excel has been on our machines for decades and is already cleared. Excel 365 added LAMBDA, which changes what you can build in it. Everything today rides on a platform that isn't going anywhere.
Don't oversell this. The point is availability and clearance, not that Excel is better than R.

## Slide 7: The Coupling Problem
Duration is uncertain (we already model this)
Phasing shape is uncertain (we usually don't)
Annual spend depends on both at once: a P50 cumulative point means different FY dollars in a 4-year execution vs. a 6-year execution
These uncertainties compound in the outyears — exactly where budget decisions live
Notes: [0:30] Motivation.
You may have had a tool pulled out from under a model. A license doesn't get renewed, a language version falls out of support, an add-in stops passing security review. When that happens the model doesn't just lose a feature — sometimes it can't be opened at all.
Excel has been on our machines for decades and is already cleared. Excel 365 added LAMBDA, which changes what you can build in it. Everything today rides on a platform that isn't going anywhere.
Don't oversell this. The point is availability and clearance, not that Excel is better than R.

## Slide 8: Proposed Solution (Preview)
Fit each completed project's normalized spend curve to a 2-parameter family
Model the fitted parameters as a population → sample new plausible curves
In Monte Carlo: draw duration + draw curve + draw cost → simulated FY-by-FY expenditure
Entire phasing model = 5 numbers per stratum (2 means, 2 SDs, 1 correlation)
Notes: [0:30] Motivation.
You may have had a tool pulled out from under a model. A license doesn't get renewed, a language version falls out of support, an add-in stops passing security review. When that happens the model doesn't just lose a feature — sometimes it can't be opened at all.
Excel has been on our machines for decades and is already cleared. Excel 365 added LAMBDA, which changes what you can build in it. Everything today rides on a platform that isn't going anywhere.
Don't oversell this. The point is availability and clearance, not that Excel is better than R.

## Slide 9: Roadmap
Motivation
Methodology
Monte Carlo Coupling
Interpreting Results
Notes: [0:30] Motivation.
You may have had a tool pulled out from under a model. A license doesn't get renewed, a language version falls out of support, an add-in stops passing security review. When that happens the model doesn't just lose a feature — sometimes it can't be opened at all.
Excel has been on our machines for decades and is already cleared. Excel 365 added LAMBDA, which changes what you can build in it. Everything today rides on a platform that isn't going anywhere.
Don't oversell this. The point is availability and clearance, not that Excel is better than R.

## Slide 10: Data and Normalization
Fit each completed project's normalized spend curve to a 2-parameter family
Model the fitted parameters as a population → sample new plausible curves
In Monte Carlo: draw duration + draw curve + draw cost → simulated FY-by-FY expenditure
Entire phasing model = 5 numbers per stratum (2 means, 2 SDs, 1 correlation)
Notes: [0:30] Motivation.
You may have had a tool pulled out from under a model. A license doesn't get renewed, a language version falls out of support, an add-in stops passing security review. When that happens the model doesn't just lose a feature — sometimes it can't be opened at all.
Excel has been on our machines for decades and is already cleared. Excel 365 added LAMBDA, which changes what you can build in it. Everything today rides on a platform that isn't going anywhere.
Don't oversell this. The point is availability and clearance, not that Excel is better than R.

## Slide 11: Roadmap
Motivation
Methodology
Monte Carlo Coupling
Interpreting Results
Notes: [0:30] Motivation.
You may have had a tool pulled out from under a model. A license doesn't get renewed, a language version falls out of support, an add-in stops passing security review. When that happens the model doesn't just lose a feature — sometimes it can't be opened at all.
Excel has been on our machines for decades and is already cleared. Excel 365 added LAMBDA, which changes what you can build in it. Everything today rides on a platform that isn't going anywhere.
Don't oversell this. The point is availability and clearance, not that Excel is better than R.

## Slide 12: Roadmap
Motivation
Methodology
Monte Carlo Coupling
Interpreting Results
Notes: [0:30] Motivation.
You may have had a tool pulled out from under a model. A license doesn't get renewed, a language version falls out of support, an add-in stops passing security review. When that happens the model doesn't just lose a feature — sometimes it can't be opened at all.
Excel has been on our machines for decades and is already cleared. Excel 365 added LAMBDA, which changes what you can build in it. Everything today rides on a platform that isn't going anywhere.
Don't oversell this. The point is availability and clearance, not that Excel is better than R.